## Budget by Activity
Activity | Description | Amount (EUR) | % of Total Budget | Timeline (Months) | FID-Funded Amount (EUR) | Co-Financing Amount (EUR) | Co-Financing Source
Hardware sourcing & terminal assembly | Procurement and assembly of PUF/ECC security chips, terminal casing, and solar mesh hub units for pilot deployment. | 70000 | 35% | Months 1-4 | 70000 | 0 | None secured yet
Technical team & field operations staffing | Personnel costs: technical lead, field coordinators, trainers, consultants for the pilot period. | 60000 | 30% | Months 1-12 | 60000 | 0 | None secured yet
Merchant/agent onboarding & field deployment | Recruitment, training, and deployment of terminals with merchants, agents, and consumers. | 30000 | 15% | Months 4-9 | 30000 | 0 | None secured yet
Field missions & travel | Travel to and within pilot deployment regions for training, monitoring, and support visits. | 15000 | 7.5% | Months 3-10 | 15000 | 0 | None secured yet
Monitoring, data collection & analysis | Transaction log analysis, FGDs/surveys, M&E reporting throughout the pilot. | 15000 | 7.5% | Months 4-12 | 15000 | 0 | None secured yet
Administrative overhead | General administrative and operational overhead costs for the pilot. | 7000 | 3.5% | Months 1-12 | 7000 | 0 | None secured yet
Contingency / other costs | Contingency buffer for unforeseen costs during pilot implementation. | 3000 | 1.5% | Months 1-12 | 3000 | 0 | None secured yet
TOTAL |  | 200000 | 100% | Months 1-12 | 200000 | 0