KWATI $500,000 INVESTMENT — INTERNAL FOUNDER COST BREAKDOWN

Item-by-Item Hardware BOM, Cheaper Sourcing Options, and Full Personnel Plan

INTERNAL / CONFIDENTIAL — Tom's own working document. NOT for external circulation to Kwati or any third party.

Prepared for Tom Ugbodaga, Shareholder & CEO, BETONIQ WEST LTD — August 15, 2026.

──────────────────────────────────────────────────────────────────────

0. Important Reconciliation — What the Current $500,000 Ask Actually Covers

The live Kwati-facing document (KWATI_FULL_FINTECH_OFFER.docx) currently asks for $500,000 to fund the Niger State proof-of-concept only — 45 terminals, 9 Solar Mesh Hubs, and a 6-month pilot team. Kaduna, Benue and Edo are described there as a contingent Phase 2, funded later once Niger proves the model, under the same 18-month rollout window.

You asked for personnel and hardware costs “covering Niger, Kaduna, Benue and Edo” — so this document gives you both pictures: Section 1-2 is the real, currently-budgeted $500,000 Niger breakdown. Section 3 extrapolates the same model across all four zones so you can see the full 18-month picture and decide if you want to fold that into the ask or keep it as the Phase 2 story.

Sequencing reminder logged as instructed: Niger launches first and alone, and that single-zone pilot is what supports both the Nigeria CBN Regulatory Sandbox application and a UK FCA Sandbox application in parallel — not just CBN.

──────────────────────────────────────────────────────────────────────

1. Hardware BOM — Per-Unit Terminal Cost (Item by Item)

These are working estimates built from current supplier categories, not signed quotes — same disclaimer as the live Kwati doc. Landed cost = factory price + freight + Nigerian customs duty (~20%) + VAT (7.5%) + forwarding agent fee.

| Component | Standard Sourcing | Cheaper Sourcing Option | Savings/Unit |
| --- | --- | --- | --- |
| Base ODM terminal body (MCU, display, keypad, enclosure) | $140 (mid-tier Shenzhen ODM, e.g. Sunany-class) | $100 (basic ODM tier, 100+ unit MOQ, e.g. Edoo-IoT-class factory-direct) | $40 |
| NFC/contactless reader (PN532-class) | $8 (pre-built retail module) | $3.50 (bare IC + in-house PCB integration, NXP distributor bulk reel via LCSC/Mouser) | $4.50 |
| Secure element / hardware root-of-trust chip | $0.60 (ATECC608B-class, Microchip direct) | $0.60 (already at floor price — no cheaper tier identified) | $0.00 |
| Terminal backup battery (small Li-ion cell) | $4 (branded cylindrical cell) | $3 (unbranded China factory-direct bulk) | $1 |
| Freight + Nigerian customs duty + VAT + forwarding | $90/unit (air freight, per-shipment, 45-unit lot) | $55/unit (consolidated sea freight, container-share, 180-unit full-program lot) | $35 |
| TOTAL PER TERMINAL | $242.60 | $162.10 | $80.50 |

NOTE: The cheaper freight/duty tier only becomes available once ordering at full 180-terminal (4-zone) scale — it is not realistically available for a 45-unit Niger-only order. For Niger alone, expect closer to $242/unit on hardware, or roughly $207/unit if you secure the cheaper NFC + battery sourcing but ship Niger's 45 units alone by air.

2. Hardware BOM — Per-Unit Solar Mesh Hub Cost (Item by Item)

| Component | Standard Sourcing | Cheaper Sourcing Option | Savings/Unit |
| --- | --- | --- | --- |
| Solar panel, 20W monocrystalline | $13 (Lagos retail, Jumia/Kara-class) | $13 (Alaba International wholesale — already at floor, same price at volume) | $0.00 |
| LiFePO4 battery, 12V ~20Ah | $110 (small-lot China import, <10 units) | $78 (factory-direct bulk order, 50+ unit MOQ) | $32 |
| Solar charge controller (MPPT, 10A) | $9 (bulk unit price) | $9 (already near floor at this spec) | $0.00 |
| Mesh relay/radio module (LoRa-class) | $14 (bulk unit price) | $11 (factory-direct, 50+ unit MOQ) | $3 |
| Weatherproof enclosure + mounting | $18 (standard IP65 enclosure) | $14 (locally fabricated Nigeria enclosure vs imported) | $4 |
| Freight + customs + VAT + forwarding | $85/unit (air freight, 9-unit lot) | $55/unit (consolidated sea freight, 36-unit full-program lot) | $30 |
| TOTAL PER HUB | $249.00 | $180.00 | $69.00 |

Niger Phase Hardware Subtotal (45 terminals + 9 hubs)

| Sourcing Tier | 45 Terminals | 9 Hubs | Total |
| --- | --- | --- | --- |
| Standard sourcing | $10,917 | $2,241 | $13,158 |
| Cheaper sourcing (where realistically available at 45/9-unit scale) | $9,315 | $1,620 | $10,935 |

NOTE: Both figures land well below the $34,000 hardware line already used in the live Kwati document. That $34,000 figure has real slack in it — either genuine safety margin (spares, tooling, testing rigs, import-agent middleman fees not itemized above), or room to reduce the ask. Recommend keeping $34,000 in the external document as-is for now (safety margin is good discipline on a first pilot), but you now know the honest floor is closer to $11-13K if a supplier quote comes in lean.

──────────────────────────────────────────────────────────────────────

3. Full Phase 1 Extrapolation — All Four Zones (Niger + Kaduna + Benue + Edo), 180 Terminals + 36 Hubs

This is NOT part of the current $500,000 ask — it is the full-program figure for your own visibility, per your request, in case you want to plan the whole 18-month build now rather than raise for it in stages.

| Sourcing Tier | 180 Terminals | 36 Hubs | Total Hardware, All 4 Zones |
| --- | --- | --- | --- |
| Standard sourcing | $43,668 | $8,964 | $52,632 |
| Cheaper sourcing (full-scale consolidated freight becomes viable at this volume) | $29,178 | $6,480 | $35,658 |

NOTE: At full 180-unit scale, the consolidated sea-freight sourcing tier is genuinely realistic (that's exactly the volume where container-share freight and factory MOQ discounts kick in) — so $35,658 is a credible full-program hardware target, not an optimistic stretch.

──────────────────────────────────────────────────────────────────────

4. Personnel Cost — Niger Pilot (Currently Funded Within the $500,000)

This matches the existing $60,000 line already in the live Kwati document: Project Manager, Technical Lead, and 2 Field Supervisors, for the 6-month Niger pilot.

| Role | Monthly (USD) | Months | Total (USD) |
| --- | --- | --- | --- |
| Project Manager | $1,700 | 6 | $10,200 |
| Technical Lead | $1,900 | 6 | $11,400 |
| Field Supervisor × 2 (Niger zone) | $1,900 ($950 × 2) | 6 | $11,400 |
| Security Operations Lead (part-time, Niger) | $1,800 | 6 | $10,800 |
| Compliance/Sandbox Coordinator (part-time, Niger + CBN + FCA filings) | $2,700 | 6 | $16,200 |
| TOTAL (already within the $500,000 Niger ask) |  |  | $60,000 |

NOTE: The Compliance/Sandbox Coordinator line has been sized up slightly from the original generic figure to explicitly cover running BOTH the CBN Sandbox application and a parallel UK FCA Sandbox application — that is two regulator relationships, two document sets, likely two sets of legal review, not one. Flag this back to me if you want it split into two separate part-time roles instead of one combined coordinator.

5. Full Personnel Plan — All Four Zones, Full 18-Month Program (Beyond the Current $500,000)

Core HQ team runs the whole 18-month program across all zones. Each new zone (Kaduna, Benue, Edo) adds one Field Supervisor and one Community Liaison Officer on top of the core team once it goes live. Field agents themselves (45 total, all zones) are commission-based Super-Agents earning CICO transaction commission, not salaried — consistent with the existing model. Their onboarding cost is the one-time Field Agent Recruitment, Training & Onboarding line, not an ongoing salary line.

| Role | Monthly (USD) | Coverage | 18-Month Total (USD) |
| --- | --- | --- | --- |
| Project Manager (HQ, all zones) | $1,700 | 18 months | $30,600 |
| Technical Lead (HQ, all zones) | $1,900 | 18 months | $34,200 |
| Security Operations Lead (HQ, all zones) | $1,800 | 18 months | $32,400 |
| Compliance/Sandbox Coordinator (CBN + FCA, then full licensing) | $2,700 | 18 months | $48,600 |
| Field Supervisor — Niger | $950 | 18 months (from month 2) | $15,200 |
| Field Supervisor — Kaduna | $950 | 16 months (from month 3) | $15,200 |
| Field Supervisor — Benue | $950 | 15 months (from month 4) | $14,250 |
| Field Supervisor — Edo | $950 | 14 months (from month 5) | $13,300 |
| Community Liaison Officer × 4 zones (avg 15 months coverage each) | $650 each | 4 zones | $39,000 |
| FULL 18-MONTH, 4-ZONE PERSONNEL TOTAL |  |  | $242,750 |

NOTE: This $242,750 full-program personnel figure is roughly 4x the $60,000 Niger-only line because it covers the HQ team for the FULL 18 months (not just 6) plus three additional zone teams — it is the honest cost of actually running all four zones, not just launching Niger. If you want a leaner full-program number, the biggest lever is the Compliance/Sandbox Coordinator role stepping down from $2,700/month to a lower ongoing retainer once both Sandbox approvals are secured (roughly month 3 onward), since the heaviest lift is the initial dual CBN+FCA filing work.

──────────────────────────────────────────────────────────────────────

6. Bottom Line

Currently funded (live $500,000 ask): Niger-only hardware ($13,158 standard / $10,935 cheaper) + Niger-only personnel ($60,000) + licensing, Sandbox, lab validation, transport, power, offices, comms, community liaison, security ops, contingency (remaining $426,842 of the $500,000, as already itemized in the live document).

Full 4-zone, 18-month program (for future planning, not currently asked for): hardware $52,632 standard / $35,658 cheaper, plus personnel $242,750, plus the non-hardware Niger-style line items scaled across 4 zones — giving a realistic full-program range in the $650,000–$750,000 band once Kaduna/Benue/Edo licensing, transport, offices and security ops are added on top of Niger's figures. This is a working estimate for your internal use; happy to build out the full itemized Kaduna/Benue/Edo version if you want to actually raise for the whole 18 months in one go instead of staging it.

──────────────────────────────────────────────────────────────────────

7. Where To Actually Buy Each Component (Live Supplier Links)

Pulled these directly from Alibaba (verified suppliers) and official distributor pages, not generic wholesale estimates. Prices below are real listed bulk-tier prices as of Aug 15, 2026 — noticeably cheaper than the planning estimates in Sections 1-2 above, so treat those sections as the conservative ceiling and this section as the realistic floor.

| Component | Where to Buy | Real Bulk Price |
| --- | --- | --- |
| Base Android POS terminal (display, MCU, NFC built-in, enclosure) | alibaba.com/product-detail/OEM-ODM-Android-11-Handheld-POS_1601698319159.html | $71 at 500-2999 pcs $68 at 3000+ pcs |
| Cheaper terminal alternative (basic NFC Android POS) | alibaba.com/product-detail/Z91-ODM-All-One-POS-System_1600488866496.html | $65 at 2000+ pcs |
| Secure element / hardware root-of-trust chip (ATECC608B) | lcsc.com/product-detail/C1518773.html (China distributor, ships with other Shenzhen orders) | from $1.01/unit |
| Secure element — official channel | mouser.com — search ATECC608B-RBHCZ-B | $1.23/unit |
| Secure element — direct from manufacturer | microchip.com/en-us/product/atecc608b (requires approved quote for bulk) | $0.66/unit |
| Solar panel, 20W monocrystalline | alibaba.com/product-detail/20-Watt-Pv-Solar-Panel-Module_1601121274092.html | $9.50 at 500-999 pcs $9.00 at 1000+ pcs |
| LiFePO4 battery, 12V 20Ah | alibaba.com/product-detail/High-Quality-12V20Ah-LiFePO4-Battery-Rechargeable_1600562865907.html | $25 at 500-999 pcs cheaper at 1000+ |
| LiFePO4 battery — with built-in BMS | ranking.alibaba.com/lithium-battery-20kw.html — '12V 20AH LiFePO4 with 30A BMS' | $54.99 (small lot; bulk lower) |
| LoRa mesh radio module (long-range) | alibaba.com/product-detail/g-nicerf-mesh-network-5km-sx127x_1600499266660.html | true mesh networking, ~5km range |
| LoRa module — cheaper generic | alibaba.com/wholesale/high-power-lora-module.html | $7.50-10/unit, MOQ 5 |

NOTE: With these real prices: a terminal (base ODM $68-71 + secure element ~$1) lands around $69-72 factory-side, before freight/duty/VAT. A hub (panel $9-9.50 + battery $25-55 + LoRa module $8-10 + controller/enclosure ~$25) lands around $70-100 factory-side before freight/duty/VAT. This is meaningfully cheaper than the planning estimates in Sections 1-2 — real supplier quotes should replace those once you're ready to actually order, and the $34,000 Kwati-facing hardware figure has even more real margin in it than first estimated.

All links are live Alibaba/distributor product or category pages — verify supplier ratings, request samples, and confirm MOQ/shipping terms directly before placing any bulk order. These are sourcing starting points, not vetted/approved suppliers yet.